## Slide 1
Enterprise IT Modernization Initiative
Top Down Service
Prioritization Roadmap
Enterprise IT Modernization Roadmap | 2025 – 2026
Delivering high-reliability microservices across all business domains
20
Total Services
Across all domains
4
Delivery Phases
2025 – Q4 2026
4
Core Domains
Loan, Payment, Fin, Comp
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 2
Executive Overview — Strategic Modernization at Scale
This roadmap captures the full service delivery lifecycle across loan, payment, financial, and compliance domains. Services are organized by delivery quarter to align engineering capacity with business priorities.
Delivery Breakdown
3
Live in Production
2025 — Completed services
7
Q1 2026 Target
Services in pipeline
6
Q2 2026 Target
Services in pipeline
4
Q3/Q4 2026 Target
Services in pipeline
Key Highlights
✓ Foundation Established
3 core services fully deployed and operational, forming the backbone of the platform.
⚡ Accelerated Delivery
13 services targeted across Q1 and Q2 2026 — the highest-velocity delivery window.
⚠ Critical Path Awareness
JMS modernization and Enabler Stories are program-level dependencies on the critical path.
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 3
✓ 2025 — Completed Services | Live in Production
All three services are fully deployed and operational — forming the backbone of the platform and the foundational layer for all subsequent service delivery.
1
PROD
Complete
Loan Disbursement Service
Core disbursement engine powering loan origination and fund release workflows.
2
PROD
Complete
Borrower Service
Manages borrower identity, profile, and lifecycle data across the platform.
3
PROD
Complete
Case Service
Handles case management, tracking, and resolution workflows for all loan cases.
These three production services represent the stable foundation upon which all Q1–Q4 2026 services will be built and integrated.
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 4
Q1 2026 — Service Delivery Pipeline
7 Services
Seven services are targeted for Q1 2026 delivery, spanning QA and active development stages. Two services carry notable dependencies requiring early resolution.
4
In QA
3
In DEV
1
Legacy Dep.
1
External Dep.
Service Name | Stage | Dependency | Notes
Business Event Service V1 | QA | — | —
Person Associations Service v1 | QA | — | —
Loan Default Service V1 | QA | Older EJB | Legacy dependency
Billing Service v1 | QA | — | —
Payment Service V2 | DEV | — | —
Credit Reporting Service V2 | DEV | External | Enabler Story required
Guaranty Rehab Service | DEV | — | —
4 Services in QA: Business Event, Person Associations, Loan Default, Billing — advancing through quality gates.
3 Services in DEV: Payment V2, Credit Reporting V2, Guaranty Rehab — in active development sprint.
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 5
Q2 2026 — Service Delivery Pipeline
6 Services
Six services are targeted for Q2 2026. Three require Enabler Stories as architectural prerequisites, and two carry JMS dependencies that must be resolved at the program level before development can begin.
Service Name | Timeline | Dependency | Notes
Person Profile Service v3 | Q2 2026 | JMS | Enabler Story required
Person Contact Service v1 | Q2 2026 | N/A | —
Direct Debit Service v1 | Q2 2026 | JMS | Enabler Story required
Repayment Schedule Service V1 | Q2 2026 | — | Enabler Story required
Consumer Tax Service v1 | Q2 2026 | — | —
IDR Forgiveness Service API V1 (REST) | Q2 2026 | — | REST API modernization
⚠ JMS Dependency Risk
Person Profile v3 and Direct Debit v1 both require JMS modernization before entering active development sprints.
📋 Enabler Story Prerequisite
3 of 6 Q2 services require Enabler Stories. Must be tracked and completed ahead of sprint assignments.
🔗 REST API Modernization
IDR Forgiveness API V1 is a key REST modernization milestone, transitioning legacy interfaces to modern standards.
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 6
Q3 / Q4 2026 — Service Delivery Pipeline
4 Services
Four services are targeted for Q3/Q4 2026 delivery. All four carry JMS dependencies and require Enabler Stories — making JMS modernization the single most critical program-level prerequisite for this phase.
Service Name | Timeline | Dependency | Notes
Person Profile Service v4 | Q3/Q4 2026 | JMS | Enabler Story required
Loan Management Service v1 | Q3/Q4 2026 | JMS | Enabler Story required
Financial Management Service V2 | Q3/Q4 2026 | JMS | Enabler Story required
Activity Service v2 | Q3/Q4 2026 | JMS over SOAP | Enabler Story required
⚠ Critical Note:
All Q3/Q4 services have JMS dependencies and require Enabler Stories to be completed first. Activity Service v2 additionally depends on JMS over SOAP — the most complex integration pattern in the roadmap. Sprint assignments will be locked following Enabler Story completion.
Person Profile
Service v4
JMS
Loan Management
Service v1
JMS
Financial Mgmt
Service V2
JMS
Activity
Service v2
JMS over SOAP
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 7
Dependency Risk Map — Risk Management
Understanding and resolving dependencies is the single most important factor in on-time delivery. Four distinct dependency categories identified across the 20-service roadmap.
1
🔗 JMS — Java Message Service
6 services depend on JMS modernization across Q2 and Q3/Q4 phases. Program-level critical path item. Ownership and timeline must be confirmed immediately.
2
📦 Older EJB — Legacy Dependency
Loan Default Service V1 carries a legacy EJB dependency. Migration planning required to unblock QA progression. Isolated risk, must be tracked actively in Q1.
3
🌐 External System Integration
Credit Reporting Service V2 relies on an external system integration. Enabler Story required; escalation to leadership recommended to confirm and contract the dependency.
4
📋 Enabler Stories — Architectural Prereqs
9 of 20 services require Enabler Stories before active development. These are architectural prerequisites and must be prioritized to avoid cascading delivery delays.
45% Enabler Dependency (9 of 20 services)
30% JMS Dependency (6 of 20 services)
15% Production Ready (3 of 20 services)
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 8
Timeline at a Glance — Full Roadmap | 20 Services across 4 Phases
✅ 2025
Complete
Loan Disbursement Service
Borrower Service
Case Service
🔵 Q1 2026
7 Services
Business Event V1
Person Associations V1
Loan Default V1
Billing V1
Payment V2
Credit Reporting V2
Guaranty Rehab
🟡 Q2 2026
6 Services
Person Profile v3
Person Contact V1
Direct Debit V1
Repayment Schedule V1
Consumer Tax V1
IDR Forgiveness API V1
🔴 Q3/Q4 2026
4 Services
Person Profile v4
Loan Management V1
Financial Mgmt V2
Activity Service v2
The roadmap follows a deliberate sequencing strategy — establishing a stable production foundation in 2025, accelerating through Q1–Q2 2026, and completing the most complex JMS-dependent services in the final phase.

## Slide 9
Delivery Principles — How We Execute
These principles govern how services move through the delivery pipeline, ensuring quality, alignment, and predictability across all program increments.
1
Stage Gate Enforcement
DEV → QA → PROD stage gates are strictly enforced before any sprint promotion. No service advances without passing the prior gate, ensuring quality is never compromised for speed.
2
Enabler Story Resolution First
All Enabler Stories must be resolved before dependent services enter active development. These architectural prerequisites are non-negotiable and must be tracked at the program level.
3
JMS on the Critical Path
JMS migration is a program-level dependency affecting 6 services across Q2 and Q3/Q4. It is on the critical path and must be owned, resourced, and tracked with the highest priority.
4
Sprint Assignment Locking
Sprint assignments for TBD services will be locked following Enabler Story completion. This prevents premature commitment and ensures capacity is allocated to ready work.
5
PI-to-Quarter Alignment
Program Increments (PIs) are mapped to calendar quarters for business alignment, ensuring engineering delivery cadence is synchronized with organizational planning cycles.
CONFIDENTIAL | Enterprise IT Modernization Initiative | Leadership Review

## Slide 10
⚑ Next Steps — Action Items for Leadership
Five critical actions must be taken by leadership to unblock the roadmap and ensure on-time delivery across all phases.
1
CRITICAL
Confirm JMS Modernization Ownership
Assign a named owner and confirm the delivery timeline for JMS modernization. 6 services across Q2 and Q3/Q4 are blocked until resolved.
2
CRITICAL
Prioritize Enabler Story Backlog
Prioritize and schedule the Enabler Story backlog for Q2 and Q3/Q4. 9 of 20 services require Enabler Stories before active development.
3
HIGH
Escalate External Dependency
Escalate the external system integration for Credit Reporting V2. Confirm partner availability, contract status, and integration timeline.
4
HIGH
Lock Sprint Assignments
Lock sprint assignments for all TBD services in the Q1 planning session. Capacity must be allocated to ready work before the quarter begins.
5
MEDIUM
Schedule Q2 2026 Readiness Review
Schedule a formal Q2 readiness review to assess Enabler Story completion, JMS migration progress, and pipeline health.
⚠ Items 1 & 2 are on the critical path and must be actioned immediately. Delays in JMS or Enabler Story prioritization cascade across Q2 and Q3/Q4 delivery timelines.